## Sheet1
S. No | Sub-Category | Observation | Identified By | Date | Status | Closing Remarks
1 | Individual House for Sale | Approval Authority has to be dropdown (Values ‘BDA’, ‘BMRDA’…). To be populated based on ‘City’ | Prasanna | 2014-07-30 | Done | Code changes done. Actual values need to be included.
2 | Individual House for Sale | Mandatory ’*’ sign can be included before the field (eg : *Title). All the fields will be properly right aligned. | Prasanna | 2014-07-30 | Done
3 | Individual House for Sale | For ‘New’ and ‘Ready to Occupy’ as ‘No’, the Expected Completion Date can be Month / Year drop down. Validation to be included. | Prasanna | 2014-07-30 | Discarded | Field 'Expected Completion Date' removed.
4 | Individual House for Sale | Bedrooms can be a dropdown | Prasanna | 2014-07-30 | Done
5 | Individual House for Sale | ‘Floor No’ has to be renamed to ‘No of Floors’. It has to be dropdown | Prasanna | 2014-07-30 | Not a Defect | This is the actual floor number where the house is present.
6 | Individual House for Sale | The options in all the dropdowns to be displayed on ‘Mouse Over’ | Prasanna | 2014-07-30 | Pending
7 | Individual House for Sale | Do we need to include a new field for Bathrooms ?? | Prasanna | 2014-07-30 | Done
8 | Individual House for Sale | Facing Direction is not mandatory. A blank option to be included in dropdown. | Prasanna | 2014-07-30 | Done
9 | Individual House for Sale | Next to ‘Price’ a check box ‘Negotiable’ to be introduced. | Prasanna | 2014-07-30 | Done
10 | Individual House for Sale | The box and shadows can be removed and the content can be displayed in full width. Font size can be increased to fit. | Prasanna | 2014-07-30 | Pending | UI to be defined.
11 | Individual House for Sale | Maximum space can be left for Image. | Prasanna | 2014-07-30 | To Be Discussed | [Shiva] Should image take more prominence over details, while posting an Ad?
12 | General | Option to add more pictures | Bharath | 2014-08-12 | Pending | Rachit is checking this out.
13 | General | Placeholder needs to be added for Title | Bharath | 2014-12-08 | Pending
14 | General | City must be dropdown (considering the numbers in the future) | Bharath | 2014-12-08 | Pending
15 | General | Area & Bedrooms can be moved above New/Resale field | Bharath | 2014-12-08 | To Be Discussed
16 | General | House Type to be added below area & bedrooms. Possible values are Independent House, Flat, Gated community Flat, Duplex, Penthouse, Villa. | Bharath | 2014-12-08 | To Be Discussed | We have merged "House Type" and "Rent/Sale" fields. We have only 7 pre-defined property types. Have to discuss how to accommodate the following: Gated Community, Duplex, Penthouse, Villa.
17 | General | Price: a. Amount entered must be immediately converted into Words like Thirty Lakhs. b. Currency needed (Rupee symbol)? | Bharath | 2014-12-08 | Pending | I have the Javascript ready (ToWords.js). The UI is disturbed when we display the amount in words. When we finalize the UI for post ad, we can take care of this as well.
18 | General | Maxlength to be set for textbox fields | Bharath | 2014-12-08 | Pending | I have done this. But need to cross-check for all pages. There could be some places where this attribute might have been overlooked.
19 | General | Remarks: As the user hits enter, can we convert it into Bullet points? I am not sure about the feasibility though. | Bharath | 2014-12-08 | To Be Discussed | It's a good feature. We've to check how it can be done. And have to check the impact on memory size.
20 | General | Amenities: Some more items can be added. Party Hall, Doctor Clinic, Super Market | Bharath | 2014-12-08 | To Be Discussed | I guess the seller can write these features in the 'Other features' box. Adding too many checkboxes too would not look good.
21 | General | EB Meter Phase field should be added. Dropdown. Values Single, Two, Three. | Bharath | 2014-12-08 | To Be Discussed
22 | General | Some fields (Area, Price) have default values. I find this as disturbing since the user needs to clear it and type. | Bharath | 2014-12-08 | Done
23 | General | Contact Details: E-Mail textbox must be added and can be populated from user profile. | Bharath | 2014-12-08 | To Be Discussed
24 | General | Apartment for sale area is left oriented. Can this be made center aligned? | Bharath | 2014-12-08 | To Be Discussed
25 | General | After clicking on Post Ad, can we provide a preview page on how his post will look before confirmation? | Bharath | 2014-12-08 | Pending | Good to have feature. Can take this up with a lower priority?
26 | General | When a huge price is entered, say ten crore, it gets converted to exponent format automatically when the post ad page is reloaded (say user has entered an invalid location and the post ad page is reloaded again - in this case, the amount entered (10 crore) appears as 10E7). | Shiva | 2014-08-31 | Defect | Need to check if we can convert double to string in jquery.
26 | General | Amounts are displayed with dots (eg 25000.0) if page is reloaded again. | Shiva | 2014-08-31 | Defect | Need to check if we can convert double to string in jquery.
26 | General | Radio button mandatory check validation in client side. | Shiva | 2014-08-31 | Defect | Java script implementation needs to be done.
26 | General | Info tips for every text box - when the user clicks on a text box, an info tool tip should be displayed indicating the purpose of the text box and a sample valid value. | Shiva | 2014-08-31 | Defect | Java script implementation needs to be done.
26 | General | Image not getting retained after post-ad page reloads. After submitting the page, if for any error, the page reloads again, the image selected by the user previously is not getting retained. | Shiva | 2014-08-31 | Defect