## Sheet1
S. No | Module | Description | Complexity | Effort (hours) | Priority | Status
1 | Home Search | In the Home search > List screen, the search text box is currently above the list. It should be moved to the side bar. | High | 10 | High | Closed
2 | Home Search | Pre-defined search keywords to be populated in DB. | Low | 8 | High | Open
3 | General | iPad compatibility. | High | ? | High | Open
4 | General | Change the logo. | High | ? | Low | Open
5 | General | A search box should be shown in all categories' list pages. | High | 10 | High | In Progress
6 | General | Currently png images are not getting uploaded properly. | High | 4 | High | Open
7 | General | Pagination should be properly working in all list screens. | High | 10 | High | Open
8 | General | Detailed plan for beta launch and post beta. Need to define timelines and acceptance criteria for beta. | High | ? | Medium | Open
9 | General | Admin Dashboard - Single screen to onboard users and create posts on behalf of them (call basis). | High | 16 | Medium | Open
10 | Header | Activate Sign In/Sign out/Dashboard links. | High | 16 | Medium | Open
11 | General | Write up for "What's Cbuddy?". | Medium | ? | Low | Open
12 | Header | Header looks awkward. Need to improve the layout. | Medium | 12 | Medium | Open
13 | General | Provision to post and search items that do not belong to any of the pre-defined 6 categories. | Medium | 16 | Medium | Open
14 | General | On mouse hover on Post Ad categories, a small tool tip should be displayed on what all items can be posted in the category. Same for each category icon in home page too. | Medium |  | Medium | Open
15 | General | Populate all dynamic data relevant to categories. | Medium | 4 | Medium | Open
16 | General | Populate Company list and the email id list. | Low | 4 | Medium | Open
17 | Details Screen | Change the Font/color. Move contact details to a different section. | Low | 4 | Medium | Open
18 | General | Populate neighborhood information. | Low | 4 | Low | Open
19 | General | Performance tuning - app/server. | Medium | 8 | Low | Open
20 | General | Moving from GoDaddy to Amazon. | Medium | ? | Low | Open
21 | Home Search | Check if newly created posts are added to the index properly and are shown in the home search results. | Low | 4 | Low | Open